Central Park Gardens

Steering Committee Meeting Agenda

11:30 am – 1:00 pm, March 18, 2009

- Updates								10 min.

  - Permanent kiosk design

  - Brochure design and text

  - Other?

- Vegetable Garden Area Improvements				15 min.

  - Pathway renovation project

  - Compost proposal

- Education Program Planning					25 min.

  - Report on February workshops

  - 2009 program calendar

  - Opportunity to list events in city recreation guide

  - Summer cooking from the garden demonstrations

  - North Davis Elementary pilot program

- Fundraising Activities						10 min.

  - Slosson proposal update

  - Ace donation request

- Upcoming Outreach Opportunities					10 min.

  - Recycled Art Fair – April 22

  - Gardeners Fair at Arboretum Plant Sale – April 25

- Long-Range Planning Calendar					15 min.

Introduce Lisa

Signboard policies

How to handle kids in the garden

Recycled Art fair

Team Exhibit Week

Compost proposal

Tool order plan

Spring and summer education programs

Long-Range Planning Calendar – Emily’s Rough Stab

Winter 2009

- Vegetable garden pathway renovation

- Plan summer and fall education programs

- Develop brochure plan and get competitive quotes

- Acquire and spread compost

- Create city compost bin proposal

- Request Ace tool donation

- Work with DF2SC partners to develop cooking demonstration pilot program

- Seek teacher input on curriculum for North Davis Elementary garden tour program

- Work with city irrigation crew to make repairs and adjustments

Spring 2009

- Kiosk fabrication and installation

- Hire design firm to create brochure, print brochure

- Plan summer education programs

- Host Recycled Art Fair – April 22

- Attend Gardeners Fair at Arboretum Plant Sale – April 25

- Plant summer vegetables

- Complete spring planting

- Mulch entire garden

- Install compost bin

- Coordinate garden tour curriculum with North Davis Elementary and implement tours

- Update plant labels for spring plantings

Summer 2009

- Plan for fall Open House

- Run summer programs

- Review North Davis Elementary tour program and decide on next steps

- Update plant labels before Open House

- Slosson grant elements:

  - Solicit design proposal for second kiosk

  - Work on concepts and content for interpretive signs

  - Work on concepts and content for cell phone tour

- Plant cool season vegetables

- Seek funds for fall planting

Fall 2009

- Hold fall Open House

- Run fall plantings

- Plan for winter and spring programs

- Plant wildflower seeds

- Prepare annual appeal letter

- Work on grant proposals as opportunities arise